## Contents
Department of Health 2024-25 Annual Report – machine readable dataset:
Capital projects completed
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2025
Capital projects reaching financial completion during the financial year ended 30 June 2025
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@health.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health annual report 2024-25, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, where the term ‘Aboriginal’ is used it refers to both Aboriginal and Torres Strait Islander people. Indigenous, First Peoples or Koori/Koorie is retained when it is part of the title of a report, program or quotation.
ISSN 2653-1852 (online)
Available at Department of Health annual report <https://www.health.vic.gov.au/department-of-health-annual-report>

## Capital projects prac. compl.
Capital projects reaching practical completion during the financial year ended 30 June 2025
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved Total Estimated Investment (TEI) Budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
A proudly multicultural Victoria | Jun. 2021 | Dec. 2024 | Dec. 2024 | The project’s cashflow was revised due to COVID-19 impacts. | 21.75 | 21.75 | 21.6 | 0.15 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Medical equipment replacement program 2022–23 (statewide) | Jun. 2023 | Dec. 2025 | Mar. 2025 | Delivery is undertaken at the health service level and implementation is dependent on delivering within and around the operational needs of the facility. | 35 | 35 | 32.69 | 2.31 | Balance of funding is required to continue to fund medical equipment replacement risk across the health system.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Jun. 2026 | Jun. 2026 | Jun. 2025 | Project was completed ahead of schedule. | 134.63 | 139.63 | 128.06 | 11.57 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Providing additional bed capacity through modular facilities (metropolitan various) | Sep. 2023 | Dec. 2024 | Jun. 2025 | Project was delayed while a suitable site to relocate the Casey modular was identified. | 54.9 | 44.9 | 44.67 | 0.23 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Rural and Regional PSRACS Revitalisation Strategy Stage 1 (regional various) | Jun. 2025 | Jun. 2025 | Jun. 2025 | No variance | 65 | 65 | 59.19 | 5.87 | Balance of funding is required for financial closeout of the project, expected in the next financial year.

## Capital projects fin. compl.
Capital projects reaching financial completion during the financial year ended 30 June 2025
Project name | Practical completion date | Financial completion date | Original approved Total Estimated Investment (TEI) budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Engineering infrastructure and medical equipment replacement program 2019–20 (statewide) | Jun. 2024 | Jun. 2025 | 60 | 60 | 57.63 | 2.37 | Project completed under budget.
Reforming Clinical Mental Health Services (Melbourne) | Aug. 2023 | Jun. 2025 | 48.1 | 34.741 | 34.19 | 0.551 | Project completed under budget.
Royal Victorian Eye and Ear Hospital Redevelopment (Melbourne) | Sep. 2024 | Jun. 2025 | 165 | 319.807 | 319.807 | 0 | Not applicable