Risk management plan documentation example

Victorian assistant workforce model – Activity 1.6

Please refer to your organisation’s risk management policies for relevant procedures relevant when developing a risk management plan for implementing the Victorian assistant workforce model (VAWM).

Table 1 below provides an example of documenting potential risks, a planned response to each risk, allocating responsibility to specific team members for implementing the response and timeframes for the responses. Allocate ratings to each potential risk according to your organisation’s risk management policy.

Table 1: Example documentation of potential risks and responses

| Example: Risk management plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Potential risk | Risk rating | Response | Responsibilities | Timeframe |
| Poor attendance at staff engagement forums / focus groups | Medium | Mitigate: Multiple communication strategies; maximise staff convenience, i.e. existing meetings; Senior support and input | Project team – entice staff to attend; prepare well; create sense of urgency; plan thoroughly including broad engagement Executive sponsor/ managers – encourage and permit staff to attend | Commencement – (insert date) |
| AHPs fear of being replaced by AHAs | High | Mitigate Change management eight steps (Kotter’s Model); frequent communication – mixed strategy; provide a clear message about the rationale for workforce reform, i.e. right person, right task/reducing lower level tasks performed by AHPs results in AHP availability for complex tasks unique to AHPs (working to full scope). | Project Team – Promote key messages early; act on issues as they arise and provide timely feedback; follow change management steps; generate support Executive Sponsor / Managers – advocate; support development of project; assist in mitigation | Commencement – ongoing |